## Test Plan Template
Test Plan Template
Test Plan Identifier: | 123
Introduction: | To define testing strategy for widget
Objectives: | Ensure that all functionalities meet specified requirements
Test Scope: | This test covers functionalities, but not system security
Date: 10/12/24 |  |  |  | Updated on: 10/12/24
Test Items | Test Environment & Tools | Test Types | Test Strategy and Approach |  | Entry Criteria | Exit Criteria | Deliverables | Start Date | End Date | Assignee | KPIs | Notes
Started | Server | functional | unit testing |  | all functional requirements must be finalized and approved | at least 95% of the planned test cases must be executed | document listing all test cases | 10.12.24 | 10.14.24 | J. Smith | test case execution rate: executed test cases/total test cases x 100
In Progress | Client machines | functional | integration testion |  | test cases must be written, reviewed and approved | a mimimum of 90% of executed test cases must pass | report summarizing outcomes of test case executions | 10.12.24 | 10.15.24 | J. Smith | pass rate: passed test cases/executed test cases x 100
Test Plan Team | [10 empty] | Related Free Templates
Name | Role | Responsibilities
J. Smith | QA | test functionality | [8 empty] | Gantt Chart Template
Dashboard Template
Task Tracker Template